## Sheet1
Defect ID | Module | Severity | Status | Reported Date | Closed Date | Assigned To | Root Cause | Resolution | Summary
BUG_011 | Login | Critical | Open | 2026-01-10 |  | Priya | Coding | Fix applied | Logo of the Website is not mentioned
BUG_001 | Dashboard | Major | Closed | 2026-01-05 | 2026-01-07 | revathi | Design | Fix applied | About us page not updated with recent address
BUG_002 | Learning | Minor | In Progress | 2026-01-08 |  | Revathi | Requirement | Deferred | Report export missing filter options
BUG_003 | Settings | Major | Closed | 2026-01-03 | 2026-01-06 | lakshmi | Coding | Fix applied | Settings not saved after update
BUG_004 | Notifications | Critical | Open | 2026-01-11 |  | durga | Environment | Workaround | Push notifications not received on Android
BUG_005 | Training | Major | Closed | 2026-01-02 | 2026-01-04 | gowtham | Design | Fix applied | Password reset link not working
BUG_006 | Reports | Minor | Open | 2026-01-09 |  | Revathi | Requirement | Deferred | Report title misaligned on print view
BUG_007 | IMPS transaction | Critical | Closed | 2026-01-01 | 2026-01-03 | lakshmi | Coding | Fix applied | Fundtransfer not updated in reports
BUG_008 | Settings | Major | In Progress | 2026-01-10 |  | durga | Environment | Workaround | Password not masked
BUG_009 | Notifications | Minor | Closed | 2026-01-06 | 2026-01-08 | gowtham | Design | Duplicate | Database flag not updated